## Master_Defect_Log
MASTER DEFECT LOG — Arattai Messenger Application ¦ QA Testing Project
Bug ID | Module | Sub-Module | Bug Title | Severity | Priority | Status | Reported By | Reported Date | Steps to Reproduce | Expected Result | Actual Result | Environment | OS Version | Fix Version | Remarks
BUG_001 | Chat | Network | Message not delivered when switching WiFi to mobile data | High | High | Closed | Harish K | 2024-01-10 | 1. Open chat 2. Send message 3. Switch from WiFi to mobile data mid-send | Message delivered or clear retry shown | Message shows 'Sent' but never delivered — silent failure | BrowserStack | Android 10 | v1.2 | Fixed in Cycle 2
BUG_002 | Group Chat | UI | Group name truncated beyond 25 chars without ellipsis | Medium | Medium | Closed | Harish K | 2024-01-11 | 1. Create group with 26-char name 2. Open group on small screen | Name truncated with '...' or wraps properly | Name cut off abruptly — no ellipsis on Android 8 | BrowserStack | Android 8 | v1.2 | Found via BVA
BUG_003 | Login | Functional | OTP field accepts alphabetic characters | High | High | Closed | Harish K | 2024-01-12 | 1. Go to OTP entry screen 2. Type 'ABCD12' in OTP field 3. Tap Verify | Field should restrict to numeric only OR show error | Alphabets accepted, no validation error shown | Local Device | Android 11 | v1.1 | Found via EP — invalid class
BUG_004 | Video Calls | Compatibility | Video feed freezes on Android 9 after camera toggle | High | High | Closed | Harish K | 2024-01-14 | 1. Start video call on Android 9 device 2. Turn camera off 3. Turn camera back on | Video resumes normally | Video freezes — requires call reconnect | BrowserStack | Android 9 | v1.3 | Not reproducible on Android 10+
BUG_005 | Media Sharing | Functional | No error shown when uploading file above 16MB | Medium | Medium | Closed | Harish K | 2024-01-15 | 1. Select a 16.1MB file 2. Tap send | Error: 'File size exceeds 16MB limit' | File upload silently fails — no user feedback | Local Device | Android 11 | v1.2 | Found via BVA boundary+1
BUG_006 | Login | Security | Session does not expire after 30 days of inactivity | Low | Low | Open | Harish K | 2024-01-16 | 1. Login 2. Do not use app for 30+ days 3. Open app | Session should expire, prompt re-login | User remains logged in indefinitely | Local Device | Android 12 | — | Security concern
BUG_007 | Chat | Functional | Delete for Everyone option missing after 7 minutes | Medium | Medium | Closed | Harish K | 2024-01-17 | 1. Send a message 2. Wait 8 minutes 3. Long press the message | 'Delete for Everyone' visible up to allowed time | Option disappears earlier than expected | Local Device | Android 11 | v1.2 | Timing threshold incorrect
BUG_008 | Group Chat | Functional | Non-admin user can see Remove Participant option | High | High | Closed | Harish K | 2024-01-18 | 1. Join group as non-admin 2. Open group info 3. Tap on a member | Remove option should be hidden for non-admins | Remove Participant option visible to all members | Local Device | Android 10 | v1.1 | Access control bug
BUG_009 | Audio Calls | Functional | Mute icon state does not update in real-time | Low | Low | Open | Harish K | 2024-01-19 | 1. Start audio call 2. Tap mute quickly multiple times | Icon updates immediately each tap | Icon lags by 1-2 seconds on slow networks | BrowserStack | Android 9 | — | UI sync issue
BUG_010 | Media Sharing | UI | Image preview distorted for portrait images in chat | Low | Low | Closed | Harish K | 2024-01-20 | 1. Send a portrait-orientation image 2. View in chat | Image shown with correct aspect ratio | Image stretched to square crop in chat bubble | Local Device | Android 11 | v1.3 | Aspect ratio not maintained

## Defect Summary
DEFECT SUMMARY
Module | Total Bugs | High | Medium | Low
Login | 3 | 2 | 0 | 1
Chat | 3 | 1 | 2 | 0
Group Chat | 2 | 2 | 0 | 0
Audio/Video Calls | 2 | 1 | 0 | 1
Media Sharing | 2 | 0 | 2 | 0
TOTAL | 12 | 6 | 4 | 2